## Excel Data
FACILITIES, INFRASTRUCTURE & COMMUNITY DEVELOPMENT
PMO/Dept-Management | Project Name | Project ID | Project Type | Council Dist. | Project Location | Project Description | FEMA PW# | AE Firm | Contractor | Total Funding | Total Estimated Costs | Current Phase | Next Phase Start
Facilities | A.L. Davis Pool Repairs | NRD155 | New Orleans Recreation Department | B | 2600 LaSalle St. |  |  | Capital Projects | TBD | 16400 | 16400 | Bid & Award | Q1 2011
Public Works | Alcee Fortier Blvd Streetscape (Chef Menteur Hwy - Michoud Lagoon) | DPW003 | Streetscapes | E | Chef Menteur Hwy - Michoud Lagoon | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Phoenix Global | Command Construction Industries, LLC | 500000 | 500000 | Bid & Award | Q1 2011
Facilities | Algiers Regional Library Design-Build | DBL001 | Public Libraries | C | 3014 Holiday Dr. | Replacement facility is designed as a wellness branch and provide all the services of the main branch including children's reading room, Wi-Fi hotspot, enterprise area and meeting rooms. | 8875 | Gibbs Construction Design-Build | Gibbs Construction Design-Build | 7944642 | 7944642 | Construction | Q4 2011
Facilities | Allie Mae Williams Multi-Service Center Phase 1 (Bldg B, D, E) | DPM005 | Health Clinics | B | 2020 Jackson Ave. | A multi-service community center requiring roof repair, paint, ceiling tile replacement, plaster ceilings, vinyl tile, repair of light fixtures and replace carpet. | 5068, 7474 | Lee Ledbetter & Associates,APC | TBD | 530423 | 530423 | Design | Q1 2011
Facilities | Arthur Monday Center/Ida Hymel Health Clinic | HCL006 | Health Clinics | C | 1111 Newton St. | Major repair/ renovation of health clinic, community services and meeting rooms. | 15520 | Chenevert Architects, LLC | TBD | 5207406 | 5207406 | Design | Q4 2011
Public Works | Audubon Blvd. (Willow St - S. Claiborne Ave) | DPW009 | Roadways | A |  | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Design Engineering, Inc. | Thigpen Construction Co., Inc. | 6138607 | 6138607 | Construction | Q2 2011
Public Works | Bayou Rd Streetscape (Broad St - Rocheblave St) | DPW010 | Streetscapes | A | Broad St - Rocheblave St | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Three Fold Consultants, Inc. |  | 700000 | 700000 | Design | Q1 2011
Facilities | Behrman Center Gym, Pool, Stadium | NRD016 | Parks & Recreation Facilities | C | 2529 General Meyer Ave. | Katrina repairs to Behrman Center Gymnasium and Pool. | 18061 | Bailey & Associates Architects, LLC | TBD | 1464088 | 1464088 | Design | Q2 2011
Facilities | Behrman Park Enhancements | NRD086 | Parks & Recreation Facilities | C | 2529 General Meyer Ave. | Behrman Stadium repairs to the football playing surface; replacement includes new artificial turf. |  | Richard C Lambert Consultants | TBD | 1700000 | 1700000 | Bid & Award | Q2 2011
Facilities | Behrman Pool Repairs | NRD157 | New Orleans Recreation Department | C | 2529 General Meyer Ave. |  |  | Capital Projects | TBD | 35400 | 35400 | Bid & Award | Q1 2011
Facilities | Behrman Soccer Complex Phase I | NRD052 | Parks & Recreation Facilities | C | 2529 General Meyer Ave. | Major site preparation and preloading for Soccer Fields |  | Sizeler Thompson Brown Architects | Southern Dredging Company, Inc. | 2996580 | 2996580 | Bid & Award | Q1 2011
Facilities | Behrman Soccer Complex Phase II | NRD136 | Parks & Recreation Facilities | C | 2529 General Meyer Ave. | Major new Soccer Stadium and Fields Complex |  | Sizeler Thompson Brown Architects | TBD | 7100000 | 7100000 | Design | Q3 2011
Public Works | Berkley Dr (Huntlee Canal - Woodland Dr) | DPW011 | Roadways | C |  | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Schrenk & Peterson | Hard Rock Construction | 6520479 | 6520479 | Construction | Q1 2012
Facilities | Brechtel Memorial Park, Golf Course, Club House, Maintenance and Cart Storage Building | RPP014 | Parks & Recreation Facilities | C | 3700 Behrman Place | Renovations to the 18-hole Golf Course, driving range and Clubhouse at Brechtel Memorial Park. | 18119 | Perez, APC | TBD | 6688362 | 6688362 | Design | Q2 2011
Facilities | Brechtel Park (Park Only) | RPP003 | Parks & Recreation Facilities | C | 3700 Behrman Place | Park, Picnic Shelters, and Campgrounds in Algiers. Renovations and repairs to shelters, restrooms, grounds, sidewalks, and bridges. | 18119, 10239 | Perez, APC | Organic Marketing | 780551 | 773060 | Contract Closure
Public Works | Broad and Washington Streetscape (S. Broad (Fourth - Louisiana) Washington (S. White - Dorgenois) | DPW313 | Streetscapes | B | S. Broad (Fourth - Louisiana) Washington (S. White - Dorgenois | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Krebs, Lasalle & Lemieux |  | 200000 | 200000 | Design | Q3 2011
Public Works | Broad St. and Lafitte St Streetscape (Bienville St - Orleans Ave) | DPW014 | Streetscapes | AB | Bienville St - Orleans Ave | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Neel - Schaffer |  | 600000 | 600000 | Design | Q2 2011
Public Works | Broadmoor Streetscape (General Pershing from Broad St. to Miro St.) | DPW016 | Streetscapes | B | General Pershing from Broad St. to Miro St. | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Krebs, Lasalle & Lemieux | 3C's Properties | 250000 | 250000 | Bid & Award | Q1 2011
Public Works | Camp St. (Canal - US 90) | DPW019 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 1574352 | 1574353 | Contract Closure
Public Works | Carondelet St. (Canal St - US 90) | DPW023 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 1433361 | 1433361 | Contract Closure
Public Works | Carrollton Ave (South) Streetscape (Palmetto St - Washington Ave) | DPW027 | Streetscapes | AB | Palmetto St - Washington Ave | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Urban Systems Associates, Inc. |  | 500000 | 500000 | Design | Q4 2011
Facilities | Carrollton Hollygrove Senior Center | NRD137 | Community Centers | A | 3300 Hamilton St. | Senior Center including health clinic and community center will be repaired/replaced. | 1812 | In-Site Developments LLC | TBD | 1969433 | 1969433 | Design | Q4 2011
Public Works | Carrollton Intersection (S. Carrollton Ave. from I-10 - Palm St.) | DPW234 | Streetscapes | AB | S. Carrollton Ave. from I-10 - Palm St. | Traffic signal and roadway intersection improvements |  | Urban Systems Associates, Inc. |  | 1500000 | 1500000 | Design | Q4 2011
Public Works | Catchbasin/Manhole Repair | PWF074 | FEMA Eligible | ABCDE |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 16575 | Richard C Lambert Consultants | Hard Rock Construction | 6891414 | 6891414 | Construction | Q3 2010
Public Works | Catina (Mouton - Robert E Lee), Louisville (Filmore - Robert E Lee) | DPW030 | Roadways | A | Catina (Mouton - Robert E Lee), Louisville (Filmore - Robert E Lee) | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Linfield Hunter & Junius | Command Construction Industries, LLC | 5332346 | 5332346
Facilities | Cemeteries | OPS173 | Other Public Spaces | ABCDE | City-wide | Repair & reconstruct masonry walls, roofs & interior repairs, repair/replace windows, and fencing repairs to citywide cemetary facilities. | 7399, 7528, 7404, 5641, 2718 | James Cripps Associated Architects, LLC | TBD | 2909639 | 2909639 | Design | Q4 2011
Facilities | Cita Hubbell Library | LIB026 | Public Libraries | C | 725 Pelican Ave. | Major renovation of roof and structure damaged by termites. | 14031 | Concordia Architects | TBD | 1372233 | 1372233 | Design | Q2 2011
Community Development | City Park Festival & Recreation Complex | NRD144 | Parks & Recreation Facilities | ABCDE | 1 Palm Dr. | Major 62-acre sports and festival complex. |  | Torre Design Consortium | TBD | 4000000 | 4000000 | Design | Q1 2011
Facilities | City-Wide Fencing | QH011 | Other Public Spaces | ABCDE | Multiple | Parks, Playgrounds, and other City Owned sites. Replacement and/or repairing of chain link, barb wire, backstop, and iron fencing at facilities, playgrounds, and fields. |  | DPM | Hamp's Construction, LLC | 769720 | 769720 | Construction | Q2 2011
Facilities | Citywide Public Safety & Criminal Justice | CJF032 | Criminal Justice Facilities | ABCDE |  |  |  | TBD |  | 54132291 | 54132291
Facilities | Civil Court Column Replacement | CJF011QH4 | Criminal Justice Facilities | B | 421 Loyola Ave. | Major structural repair of (2) Ground Floor columns |  | Wink Design Group | Lathan Construction | 148793 | 148793 | Closeout
Public Works | Claiborne (South) @ Toledano (Napoleon Ave - Martin Luther King Jr.) | DPW178 | Streetscapes | B | Napoleon Ave - Martin Luther King Jr. | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | All South | F.H, Paschen, SN. Nielsen & Associates LLC | 2000000 | 2000000 | Bid & Award | Q2 2011
Public Works | Claiborne Ave (Esplanade Ave- St. Anthony St) | DPW038 | Streetscapes | C | Esplanade Ave- St. Anthony St | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Buchart Horn |  | 300000 | 300000 | Design | Q2 2011
Public Works | Claiborne Avenue Streetscape (Cleveland St. - Gravier St.) | DPW089 | Streetscapes | B |  | Sidewalk and landscaping improvements |  | Urban Systems Associates, Inc. | RMD Holdings Ltd | 1988802 | 1988802 | Contract Closure
Facilities | Comiskey Park | NRD021 | Parks & Recreation Facilities | B | 600 S. Jefferson Davis Pkwy. | Renovations of the NORD operated park and associated play equipment. |  | John Williams Architects | TBD | 500000 | 500000 | Design | Q2 2011
Facilities | Comiskey Playground | NRD109 | Parks & Recreation Facilities | B | 600 S. Jefferson Davis Pkwy. | Renovations to playground high mast lighting and electrical equipment, and renovations to concessions building. | 3282, 1730 | Terrell-Fabacher Architects, LLC | TBD | 293168 | 293168 | Design | Q1 2011
Public Works | Common St. (Loyola Ave - S. Peters St) | DPW041 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 2394115 | 2394117 | Contract Closure
Public Works | Countdown Timers - Downtown | DPW285 | Roadways | B |  | Install new pavement markings and signage |  |  |  | 495000 | 495000 | Planning | Q1 2011
Public Works | Countdown Timers - Poydras | DPW286 | Roadways | B |  | Install new pavement markings and signage |  |  |  | 495000 | 495000 | Planning | Q1 2011
Facilities | Criminal District Courts / Two New Courtrooms | CJF012 | Criminal Justice Facilities | B | 2700 Tulane Ave. | Major interior renovation to relocate two courts. |  | Sizeler Thompson Brown Architects | TBD | 5755800 | 5755800 | Design | Q2 2011
Public Works | Crowder Boulevard (Dwyer Rd - US 90) Bikeways | DPW250 | Roadways | E |  | Install new pavement markings and signage |  | Department of Public Works | Gulf Industries / Vulcan Industries | 10560 | 10560 | Construction | Q1 2011
Facilities | Cut Off Center | OPS033 | Community Centers | C | 6600 Belgrade St. | Algiers Community Center ; renovations and repairs to facility interior and grounds improvements. | 2387 | St Martin Brown & Associates, LLP | Batco Construction & Maintenance, Inc. | 626417 | 603256 | Construction | Q2 2011
Facilities | Desire/Florida Multi-Service Center & Helen Levy Clinic Alternate | HCL010 | Health Clinics | E | 2727 Louisa St. | New construction of shared multipurpose community center. | 3779 | TBD | TBD | 11787738 | 11787738 | Planning | Q2 2011
Facilities | Di Benedetto Playground | NRD063 | Parks & Recreation Facilities | E | 4700 Papania St. | Playground repairs. | 4860, 2437 | St Martin Brown & Associates, LLP | TBD | 311948 | 311948 | Planning | Q2 2011
Facilities | Digby Park | NRD141 | Parks & Recreation Facilities | D | 6600 Virgilian St. | Playground Improvements. | 8036 | TBD | TBD | 112969 | 112969 | Planning | Q2 2011
Facilities | Donnelly Playground Equipment Donation | NRD146 | Parks & Recreation Facilities | D | Burbank Drive and Wildair Dr. | Surface installation for work & equipment donation program. |  | TBD | TBD | 30000 | 30000 | Closeout
Public Works | Dr. Charles R. Drew Elementary - Safe Routes to School (K08-572) State ID 737-99-1024 | DPW287 | Roadways | C |  | Install new pavement markings and signage |  | ECM Consultants, Inc |  | 250000 | 250000 | Design | Q1 2012
Public Works | Drain Point Repair Services | DPW321 | FEMA Eligible | ABCDE |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 18920 | Richard C Lambert Consultants | Boh Brothers Construction Company, L.L.C. | 4687782 | 4687782 | Construction | Q1 2011
Public Works | Drainage Master Plan Study | DPW293 | Other | ABCDE |  | Conduct field investigations and survey of major drainage facilities. Review and update existing Geographic Information System (GIS) data. Review and assess current data management, develop model for new system. Develop standards and guidelines, and maintenance procedures. |  | Camp, Dresser & McKee, Inc. |  | 2000000 | 2000000 | Design
Public Works | Earhart Blvd Phase I (Hamilton St - Fern St) | DPW050 | Roadways | AB |  | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Buchart Horn | Command Construction Industries, LLC | 12072358 | 12072356 | Construction | Q1 2011
Facilities | Easton Playground Equipment Donation | NRD147 | Parks & Recreation Facilities | A | 600 Lopez St. | Surface installation for work & equipment donation program. |  | TBD | TBD | 35000 | 35000 | Closeout
Public Works | Edgelake Court (Crowder Rd - Hayne Blvd) | DPW329 | Roadways | D |  | Asphalt pavement, base repair and curb replacement |  |  | Boh Brothers Construction Company, L.L.C. | 338900 | 338900 | Construction | Q4 2010
Public Works | Elysian Fields (Lakeshore Dr. - Gentilly Blvd. / US 90) | DPW052 | Roadways | D |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | RMD Holdings Ltd | 6170708 | 6170708 | Construction | Q2 2011
Public Works | Esperanza Charter School - Safe Routes to School (K09-886) State ID 737-99-1024 | DPW314 | Roadways | A |  | Install new pavement markings and signage |  | ECM Consultants, Inc |  | 250000 | 250000 | Design | Q4 2012
Facilities | FFE for Design Build Libraries | DBL008 | Public Libraries | ACDE | Various | Supplying contents for the 5 Design-Build Libraries. | 8875, 7500, 7579, 11769, 7421 | Contract Furniture Group | Contract Furniture Group | 5299692 | 5299692 | Planning | Q1 2011
Public Works | Filmore Ave (St. Bernard Ave - Elysian Fields Ave) | DPW055 | Roadways | D |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | RMD Holdings Ltd | 3243319 | 3243319 | Construction | Q2 2011
Public Works | Fleur de Lis Phase II (Veterans Blvd - Harrison Ave) | DPW058 | Roadways | A |  | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Krebs, Lasalle & Lemieux | Boh Brothers Construction Company, L.L.C. | 11772501 | 11772501 | Construction | Q1 2011
Public Works | Freret St Streetscape (Napoleon Ave - Jefferson Ave) | DPW063 | Streetscapes | B | Napoleon Ave - Jefferson Ave | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | M&S Eng. Collaborative | F.H, Paschen, SN. Nielsen & Associates LLC | 500000 | 500000 | Bid & Award | Q2 2011
Facilities | Gallier Hall Fire Damage | DPM004 | Community Centers | B | 545 Saint Charles Ave. | Repair of fire damage to the rear of Gallier Hall. | 4466 | TBD | TBD | 117000 | 117000 | Design | Q1 2011
Facilities | Gallier Hall Renovations | DPM008 | Community Centers | B | 545 Saint Charles Ave. | Major repairs to existing roof and interior. | 4466 | Imre Hegedus and Associated Architects | Kevin J. Smith Construction | 1308795 | 1308795 | Contract Closure
Public Works | Galvez St (Elysian Fields Ave - Almonaster Ave ) | DPW067 | Roadways | D | (Elysian Fields Ave - Almonaster Ave ) | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Shaw Environmental and Infrastructure |  | 5313000 | 5313000 | Design | Q2 2011
Public Works | Galvez St (Tennessee St - Delery St) | DPW130 | Roadways | E | (Tennessee St - Delery St) | Reconstruction of existing roadway, including the replacement of affected utilities. |  | N-Y Associates Architects | N-Y Associates, Inc. | 8079480 | 8079480 | Design | Q3 2011
Public Works | General Meyer Ave Streetscape (Hendee St - Odeon Ave) | DPW054 | Streetscapes | C | Hendee St - Odeon Ave | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | M&S Eng. Collaborative |  | 500000 | 500000 | Design | Q2 2011
Public Works | Gentilly Minor Streets - Caton (Gentilly Blvd. - Norman Mayer Ave.), Touro (Caton - Senate) | DPW070 | Roadways | D |  | Improvements to various minor streets, which may include reconstruction and/or milling and overlay. |  | Department of Public Works |  | 452120 | 452120 | Bid & Award | Q2 2011
Public Works | Gentilly Streetscape (Caton, Gentilly, Elysian Fields) | DPW071 | Streetscapes | D | Caton, Gentilly, Elysian Fields | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Three Fold Consultants, Inc. |  | 700000 | 700000 | Bid & Award | Q2 2011
Facilities | Gernon Brown Gym | NRD029 | Parks & Recreation Facilities | A | 1001 Harrison Ave. | Repairs to an existing NORD gymnasium, including a gym space and multipurpose room. | 17713 | TBD | TBD | 1902812 | 1902812 | Contracting | Q1 2011
Facilities | Gert Town Community Pool | NRD138 | Community Centers | B | 7400 Stroelitz St. | Replacement of former pool facility serving the Hollygrove neighborhoods. | 3802 | Linfield Hunter & Junius | TBD | 1923639 | 1923639 | Design | Q3 2011
Facilities | Gert Town Pool Demolition | NRD124 | Parks & Recreation Facilities | B | 7400 Stroelitz St. | Demolition of the current Gernon Brown pool facility. | 3802 | Department of Sanitation | TBD | 100000 | 100000 | Design | Q1 2011
Public Works | Girod St. (Loyola Ave - S. Peters St) | DPW074 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 1052794 | 1052794 | Contract Closure
Public Works | Gordon (Chartres - St. Claude), Flood (Peters - St. Claude) | DPW075 | Roadways | E |  | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Burk-Kleinpeter, Inc | Burk-Kleinpeter, Inc | 5991266 | 5991266 | Construction | Q3 2011
Public Works | Gravier St (Galvez - Broad) | DPW076 | Roadways | B | (Galvez - Broad) | Reconstruction of existing roadway, including the replacement of affected utilities. |  | ECM Consultants, Inc |  | 3381000 | 3381000 | Design | Q1 2011
Public Works | Gravier St. (Loyola Ave - S. Peters St) | DPW077 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 810997 | 810997 | Contract Closure
Facilities | Harrell Stadium, Center, & Pool | RPP004 | Parks & Recreation Facilities | A | 2300 Leonidas St. | Hollygrove Community Center, Pool, and Pool House; existing building(s) to receive renovations and repairs; new chlorination system for pool. | 6113, 2245, 4607,2059 | Mathes Brierre Architects, APC | Crescent Commercial Const | 800048 | 800048 | Construction | Q2 2011
Public Works | Harrison Ave Bridge over Bayou St. John (Eastbound) | DPW081 | Roadways | AD |  | Bridge reconstruction |  | Rahman & Associates | Thigpen Construction Co., Inc. | 1414992 | 1414992 | Construction | Q2 2011
Public Works | Harrison Ave Bridge over Bayou St. John (Westbound) | DPW082 | Roadways | AD |  | Bridge reconstruction |  | Rahman & Associates | Thigpen Construction Co., Inc. | 1159664 | 1159664 | Construction | Q2 2011
Public Works | Harrison Ave Streetscape (West End Blvd - Orleans Ave) | DPW083 | Streetscapes | A | West End Blvd - Orleans Ave | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Torre Design Consortium |  | 4000000 | 4000000 | Design | Q2 2011
Public Works | Holiday Dr (General Meyer Ave - MacArthur) | DPW085 | Roadways | C |  | Rehabilitation of roadway by milling existing surface and overlay with new asphalt, including pre-milling patching repairs as well as adjustment of utility manholes, where applicable. |  | Professional Engineering Consultants | Barriere Construction Co. | 5518148 | 5518148 | Bid & Award | Q1 2011
Public Works | Holiday Dr (MacArthur - Behrman) | DPW086 | Roadways | C | (MacArthur - Behrman) | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Rahman & Associates | TBD | 4554000 | 4554000 | Design | Q1 2011
Public Works | Holy Cross Roadway Improvements - Douglass St., Andry St., N. Peters St. | DPW245 | Roadways | E |  | Improvements to various minor streets, which may include reconstruction and/or milling and overlay. |  | Department of Public Works | Julien Engineering & Consulting, Inc. | 2500000 | 2500000 | Contract Closure
Public Works | Howard Avenue Ext. (Loyola Ave - LaSalle St) | DPW088 | Roadways | B | (Loyola Ave - LaSalle St) | Improvements to various minor streets, which may include reconstruction and/or milling and overlay. |  | Meyer Engineers |  | 7475000 | 7475000 | Design | Q1 2012
Facilities | Hunter's Field | NRD031 | Parks & Recreation Facilities | C | 1600 North Claiborne Ave. | 7th ward shared community field space adjacent to the Treme neighborhood. Repair of field and minor concession building renovation. | 13790 | Bailey & Associates Architects, LLC | TBD | 1614128 | 1614128 | Design | Q3 2011
Facilities | Joe Brown Center | NRD006 | Parks & Recreation Facilities | E | 5601 Read Blvd. | Part of the Joe Brown Park renovation. Multipurpose community center. Large interior renovation of facility. | 3294 | Bailey & Associates Architects, LLC | TBD | 3835841 | 3835841 | Design | Q3 2011
Facilities | Joe Brown Indoor Pool | NRD033 | Parks & Recreation Facilities | E | 5601 Read Blvd. | Indoor Pool. Existing facility and site to receive major renovations and repairs to interior of bath house. Pool to be repaired and receive new chlorination system. | 3868 | Linfield Hunter & Junius | Ryan Gootee General Contractors | 3274954 | 3274954 | Construction | Q2 2011
Facilities | Joe Brown Park Enhancements | NRD085 | Parks & Recreation Facilities | E | 5601 Read Blvd. | Part of the Joe Brown Park renovation in New Orleans East. Major added ground enhancements to the existing facility. |  | Billes Architecture, LLC. | TBD | 4000000 | 4000000 | Design | Q4 2011
Facilities | Joe Brown Park Lighting, Ball Fields, Shelters | NRD034 | Parks & Recreation Facilities | E | 5601 Read Blvd. | Major repairs to baseball fields, park grounds, and shelters. | 18072 | ECM Consultants, Inc | TBD | 10730604 | 10730604 | Design | Q2 2011
Facilities | Joseph Bartholomew Club House & Maintenance Warehouse Building | RPP006 | Parks & Recreation Facilities | D | 6514 Congress Dr. | Part of the Ponchartrain Park community golf course renovation. Repair of 1st tee (Hole 1) concessions building. | 18043, 18049 | Perez, APC | TBD | 2173211 | 2173211 | Design | Q2 2011
Facilities | Joseph Bartholomew Golf Course (Pontchartrain Park) | RPP005 | Parks & Recreation Facilities | D | 6514 Congress Dr. | Complete renovation of existing golf course | 18043 | Perez, APC | Duinick Inc. | 9090791 | 9090791 | Contract Closure
Facilities | Joseph Bartholomew Youth Golf Education Center (1st Tee Program) | RPP012 | Parks & Recreation Facilities | D | 6514 Congress Dr. | Part of the Ponchartrain Park community golf course renovation. Repair of 1st tee (Hole 1) concessions building. |  | Perez, APC | TBD | 1000000 | 1000000 | Design | Q4 2011
Community Development | Lafitte Greenway Land Acquisition & Development | NRD143 | Parks & Recreation Facilities | ABC | Treme to Canal Blvd. | Linear Park Development |  | TBD | TBD | 4000000 | 4000000 | Bid & Award | Q2 2011
Public Works | Lafitte Greenway/Lafitte GW Corr. Bikepath-(Broad - Jeff Davis) | DPW094 | Streetscapes | A |  | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Design Workshop, Inc. | TBD | 8000000 | 8000000 | Contracting | Q1 2010
Public Works | Lakefront/Holy Cross Traffic Signals | DPW098 | Roadways | A |  | Traffic signal improvements |  | AECOM |  | 1250000 | 1250000 | Design | Q1 2011
Public Works | LaSalle St (Poydras - Tulane Ave US 61) | DPW100 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 1182707 | 1182707 | Contract Closure
Facilities | Latter Library | LIB008 | Public Libraries | B | 5120 St. Charles Ave. | Termite repairs on main house and carriage house. | 8904 | Concordia Architects | TBD | 1359373 | 1326162 | Design | Q3 2011
Facilities | Latter Library HVAC Repairs | LIB035 | Public Libraries | B | 5120 St. Charles Ave. | Repair of the HVAC system at the Latter Library facility. |  | Concordia Architects | TBD | 366366 | 366366 | Design | Q2 2011
Facilities | Latter Library Roof Replacement | LIB033 | Public Libraries | B | 5120 St. Charles Ave. | Replace historic claytile roof. | 8904 | Concordia Architects | CMR Construction & Roofing | 968851 | 968851 | Contract Closure
Public Works | LeBoeuf (Patterson - Opelousas), Sumner (Newton - Opelousas), Slidell (Whitney - Sumner) | DPW101 | Roadways | C |  | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Rahman & Associates | Barriere Construction Co. | 4648674 | 4648674 | Construction | Q4 2011
Facilities | Leman Pool Repairs | NRD099 | New Orleans Recreation Department | B | 536 N Prieur St |  | 3858, 1730 | Capital Projects | TBD | 20400 | 20400 | Bid & Award | Q1 2011
Public Works | Leon C. Simon Dr (London Canal - Elysian Fields Ave) | DPW102 | Roadways | D |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | RMD Holdings Ltd | 1625463 | 1625463 | Construction | Q2 2011
Facilities | Louis Armstrong Park (Phase 2) | DPM011 | Parks & Recreation Facilities | C | 901 N Rampart St | Repairs to park. |  | John Williams Architects | Peabody Construction | 2799233 | 2799233 | Construction | Q3 2011
Facilities | Louis Armstrong Park (Phase 3) | DPM009 | Parks & Recreation Facilities | C | 901 N Rampart St. | Continue the renovation of the park including the relocation of the Louis Armstrong Statue and the installation of 7 other statues dedicated to cultural contributions. |  | Hamilton Anderson Associates, Inc. | AME Disaster Recovery Services, Inc. | 4992805 | 4992805 | Construction | Q2 2011
Public Works | Lower Ninth Ward Streetscape (N. Claiborne - Andry to Lamanche) (St. Claude -Bridge to Egania) | DPW106 | Streetscapes | E | N. Claiborne - Andry to Lamanche, and St. Claude -Bridge to Egania | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Neel - Schaffer |  | 1900000 | 1900000 | Design | Q2 2011
Public Works | Loyola Ave. (Canal St. - US 90) | DPW108 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 5490739 | 5490739 | Contract Closure
Facilities | Lyons Center | NRD008 | Community Centers | B | 624 Louisiana Ave. | Major renovations of Hurricane Katrina related damage at the NORD operated pool and gymnasium facility located in the Irish Channel. | 7703 | Wayne Troyer Architects | TBD | 2607850 | 2607850 | Design | Q1 2011
Facilities | Lyons Pool Repairs | NRD162 | New Orleans Recreation Department | B | 715 Delchaise St. |  |  | Capital Projects | TBD | 24000 | 24000 | Bid & Award | Q1 2011
Public Works | Magazine St. (Canal - US 90) | DPW113 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 1104237 | 1104237 | Contract Closure
Public Works | Magazine St. (US 90B - Nashville) | DPW114 | Roadways | AB |  | Rehabilitation of roadway by milling existing surface and overlay with new asphalt, including pre-milling patching repairs as well as adjustment of utility manholes, where applicable. |  | Meyer Engineers | Plus Concrete, Inc. | 6650773 | 6650773 | Construction | Q4 2011
Public Works | Marconi Blvd. (Robert E. Lee - Norfolk Southern Railroad) Bikeways | DPW249 | Roadways | AC |  | Install new pavement markings and signage |  | Department of Public Works | Gulf Industries / Vulcan Industries | 27225 | 27225 | Construction | Q2 2010
Public Works | Martin Bridge over Morrison | DPW118 | Roadways | D |  | Bridge reconstruction |  | Shaheen |  | 835200 | 835200 | Bid & Award | Q2 2011
Public Works | Michoud Front Door Infrastructure Improvements (Old Gentilly Road from I5-10 - Chef Menteur Highway) | DPW142 | Roadways | E | Old Gentilly Road from I5-10 - Chef Menteur Highway | Various street improvements near the New Orleans Regional Business Park |  | Stuart Consulting Group, Inc. |  | 6254298 | 6254298 | Contracting | Q1 2011
Facilities | Milne Boys Home | OPS003 | City Facility | D | 5420 Franklin Ave. | Hurricane Katrina Renovations of the historic Gentilly Facility with multiple buildings. | 12754, 13521, 18095 | Waggoner & Ball Architects | TBD | 12486711 | 12486711 | Design | Q3 2011
Public Works | Mirabeau Ave (St. Bernard Ave - Elysian Fields Ave) | DPW128 | Roadways | D |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | RMD Holdings Ltd | 3576398 | 3576398 | Construction | Q2 2011
Public Works | Miro St (Elysian Fields Ave - Orleans Ave) | DPW129 | Roadways | ACD |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | Boh Brothers Construction Company, L.L.C. | 1394837 | 1394837 | Construction | Q2 2010
Facilities | Mosquito Control Administration Building Design-Build | DBL006 | City Facility | D | Leon C. Simon Blvd @ Elysian Field Ave. | Replacement and relocation of mosquito and rodent control facility. | 1391,1806, 2042, 1508, 2058, 10684, 12575 | Woodward Design-Build | Woodward Design-Build | 5283430 | 5283430 | Construction | Q3 2011
Facilities | Mosquito Control Hangar | MTC002 | Other Public Spaces | D | 6001 Stars & Stripes Blvd |  | 12125, 1485, 2060 | Three Fold Consultants, Inc. | TBD | 980738 | 980738 | Design | Q1 2011
Facilities | Municipal Traffic Courts (Phase 2) - LED | CJF024 | Criminal Justice Facilities | B | 727 S Broad St. | Comprehensive renovation and 3rd floor build-out of the Municipal Traffic Courts that also includes selective improvements to building systems. Renovation and build-out with double the current available space. |  | Pascal Architects LLC | TBD | 10609000 | 10609000 | Design | Q1 2012
Facilities | Municipal Yacht Harbor Administration Building Repairs | OPS006 | Parks & Recreation Facilities | A | 401 N. Roadway St. | MYH and NOYC shared offices and multi use meeting space located in Bucktown/Lakeview. Medium project - Building will undergo complete renovation to first floor interior and some minor exterior repair work. | 7396 | Sizeler Thompson Brown Architects | Precision Construction | 1259912 | 1259912 | Construction | Q1 2011
Facilities | Municipal Yacht Harbor Boat House Repairs | OPS009 | Parks & Recreation Facilities | A | 401 N. Roadway St. | NO Fire Department Boat House and MYH Boat Slip. Small project - Repair of both structures and renovation of interior living quarters of NOFD boat house. | 11803 | Sizeler Thompson Brown Architects | TBD | 298316 | 298316 | Design | Q2 2011
Facilities | Municipal Yacht Harbor Repairs | OPS004 | Parks & Recreation Facilities | A | 401 N. Roadway St. | Includes Piers, Bulkheads, and Pilings. Large project located in Bucktown/Lakeview – Repair of entire harbor facility to restore functionality to all rental boat slips that are currently damaged. | 18042, 13892 | Sizeler Thompson Brown Architects | TBD | 27527925 | 27527925 | Design | Q3 2011
Public Works | N. Galvez (Orleans Ave. - Poydras) | DPW289 | Roadways | AB |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | Boh Brothers Construction Company, L.L.C. | 3309167 | 3309167 | Construction | Q3 2011
Public Works | Napoleon, Broad and Fontainebleau Intersection Design | DPW238 | Streetscapes | B |  | Interim repairs have been completed by volunteers and fire fighters. However, some minor repairs, including architectural and mechanical systems, remain and must be further defined during the AE scoping exercise. |  | Urban Systems Associates, Inc. |  | 250000 | 250000 | Contracting | Q1 2011
Public Works | Napoleon-Freret Roadway Improvements (Clara St. (Napoleon - Cadiz), Jena (Clara - S. Claiborne)) | DPW290 | Roadways | B |  | Improvements to various minor streets, which may include reconstruction and/or milling and overlay. |  | Department of Public Works | Julien Engineering & Consulting, Inc. | 855300 | 855300 | Construction | Q3 2011
Public Works | Nashville Ave (Claiborne US 90 - Tchoupitoulas St) | DPW131 | Roadways | A |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Meyer Engineers | Barriere Construction Co. | 5685665 | 5685665 | Contract Closure
Public Works | Navarre Ave. (Canal Blvd. - Marconi Dr) | DPW132 | Roadways | A |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | Boh Brothers Construction Company, L.L.C. | 808592 | 808592 | Construction | Q3 2010
Community Development | New Orleans East Community Health Clinic | HCL014 | Health Clinics | E | 13085 Chef Menteur Hwy. | New community center health clinic. |  | TBD | TBD | 1100000 | 1100000 | Design | Q4 2011
Community Development | New Orleans East Hospital Land Acquisition & Development | HSP001 | Hospital Facility | E | 5620 Reed Blvd. | Major acquisition/renovation of existing Methodist Hospital. |  | TBD | TBD | 40000000 | 40000000 | Planning | Q1 2011
Facilities | New Orleans East Regional Library Design-Build | DBL005 | Public Libraries | E | 5641 Read Blvd | Replacement facility is designed as a "Technology/ Innovation Branch" and includes the same services as the main branch including children's reading room, Wi-Fi hotspot, enterprise area and meeting rooms. | 7500 | Gibbs Construction Design-Build | Gibbs Construction Design-Build | 7553153 | 7553153 | Construction | Q3 2011
Public Works | New Orleans East Streetscape Improvements (Read Blvd, Lakeforest Blvd, Crowder Rd) | DPW239 | Streetscapes | E | Read Blvd, Lakeforest Blvd, Crowder Rd | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Phoenix Global |  | 3000000 | 3000000 | Design | Q2 2011
Facilities | New Orleans Museum Exterior | OPS199 | Other Public Spaces | A | 1 Collins Diboll Cir. |  |  | TBD | TBD | 1000000 | 1000000 | Planning | Q1 2011
Facilities | New Orleans Museum of Art Damage Repairs | OPS166 | Community Centers | A | 1 Collins Diboll Cir. | Renovations to NOMA facilities | 15936 | Eskew, Dumez & Ripple | TBD | 3358798 | 3358798 | Design | Q3 2011
Facilities | NOFD Engine 10 Morrison Rd. | NFD008 | New Orleans Fire Department | E | 14069 Morrison Road | Renovation of the Morrison Avenue Fire Station No. 10, including equipment bay and living quarters for firemen. | 8688 | Three Fold Consultants, Inc. | TBD | 368053 | 368053 | Bid & Award | Q2 2011
Facilities | NOFD Engine 26 S. Jefferson Davis Pkwy. | NFD024 | New Orleans Fire Department | B | 436 S Jefferson Davis Pkwy. | Repairs to bay equipment and living quarters. | 9833 | TBD | TBD | 246720 | 246720 | Contracting | Q2 2011
Facilities | NOFD Engine 31 Alba Rd. | NFD026 | New Orleans Fire Department | E | 4300 Alba Road | Replacement of the Venetian Isle Fire Station No. 31, including 2 equipment bays and living quarters for firemen. | 1096 | Trapolin Architects, APC | TBD | 2871815 | 2871815 | Design | Q3 2011
Facilities | NOFD Engine 40 Gen. DeGaulle | NFD031 | New Orleans Fire Department | C | 2500 General DeGaulle Dr | Major renovation to include mold remediation and repairs to interior of the fire station, dormitories, and other spaces. | 1103 | TBD | TBD | 154110 | 154110 | Design | Q2 2011
Facilities | NOFD Engine Nos. 22 and 03 | NFD020 | New Orleans Fire Department | E | N Claiborne Ave & Caffin Ave | New combined 2-company, 3-bay fire station complete with living quarters for firemen. | 9750, 1051 | Trapolin Architects, APC | TBD | 3453184 | 3453184 | Design | Q3 2011
Facilities | NOPD Fifth District Police Station | NPD006 | New Orleans Police Department | C | 3900 N Claiborne | New construction for the replacement of the NOPD 5th District Police station on the original Claiborne Avenue site. | 8483 | Imre Hegedus and Associated Architects | TBD | 7480816 | 7480816 | Design | Q2 2011
Facilities | NOPD Police Stables | NPD018 | New Orleans Police Department | A | Harrison Avenue & Marconi Dr. | NOPD's Stables in City Park are scheduled to be repaired to better house the City's Mounted Patrol Horses and K9 dogs. The stables provide space for the NOPD Horses used to patrol Mardi Gras and special events. | 11834 | SCNZ Architects, LLC | TBD | 6103124 | 6103124 | Design | Q2 2011
Facilities | NOPD Seventh District Police Station | NPD008 | New Orleans Police Department | E | 10101 Dwyer Road | New elevated 2-story Police Station for the Seventh District NOPD, located on the original Read Blvd. site. | 19038 | Imre Hegedus and Associated Architects | Construction Masters | 6508427 | 6508427 | Construction | Q3 2011
Facilities | NOPD Special Operations Division | PSF009 | New Orleans Police Department | B | 1899 Tchoupitoulas St. | Build-out of office and support space within the NOPD Special Operations Division warehouse; this facility consolodates the SWAT, Traffic and Street Crimes Divisions of the NOPD. |  | Steven J. Finegan Architect, Ltd. | Kemper Construction Company Inc. | 2798667 | 2798667 | Contract Closure
Facilities | Nora Navra Library Demolition | LIB029 | Public Libraries | C | 1902 St. Bernard Ave. | Demolition of the current library. | 11769 | Department of Sanitation | TBD | 100000 | 100000 | Design | Q1 2011
Facilities | Nora Navra Library Design-Build | DBL002 | Public Libraries | D | 1902 St. Bernard Ave. | Replacement facility will be in a new location and is designed as a "Neighborhood Branch" to include meeting rooms, enterprise space and a basic collection. | 11769 | Gibbs Construction Design-Build | Gibbs Construction Design-Build | 2950703 | 2950703 | Construction | Q4 2012
Facilities | NORD High Mast Lighting - Bodenger Playground | NRD167 | Parks & Recreation Facilities | C | 3000 Memorial Park Drive |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 105946 | 105946 | Bid & Award | Q1 2011
Facilities | NORD High Mast Lighting - Di Benedetto Playground | NRD168 | Parks & Recreation Facilities | E | 4700 Papania St. |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 103828 | 103828 | Bid & Award | Q1 2011
Facilities | NORD High Mast Lighting - Digby Playground | NRD164 | Parks & Recreation Facilities | D | 6600 Virgilian St. |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 95408 | 95408 | Bid & Award | Q1 2011
Facilities | NORD High Mast Lighting - Donsereaux/Harrison Playground | NRD165 | Parks & Recreation Facilities | C | 3100 DeArmas Street |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 70828 | 70828 | Bid & Award | Q1 2011
Facilities | NORD High Mast Lighting - Harris Playground | NRD169 | Parks & Recreation Facilities | D | 4983 Louisa St |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 209878 | 209878 | Design | Q1 2011
Facilities | NORD High Mast Lighting - Hunter's Field | NRD166 | Parks & Recreation Facilities | C | 1600 North Claiborne Ave. |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 113828 | 113828 | Bid & Award | Q1 2011
Facilities | NORD High Mast Lighting - Norman Playground | NRD163 | Parks & Recreation Facilities | C | 3201 Eton St. |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 53990 | 53990 | Design | Q1 2011
Facilities | NORD High Mast Lighting Group 1 | NRD111 | Parks & Recreation Facilities | ABCDE | Various | High Mast Lighting; Replacement or additions of new timber poles, lighting fixtures, electrical boxes, wiring, and bulbs at playgrounds, parks, ball fields, and community areas. | 12858, 10746, 4930, 3877, 2387 | Three Fold Consultants, Inc. | Frischhertz Electric | 304255 | 304255 | Contract Closure
Facilities | NORD High Mast Lighting Group 2 | NRD112 | Parks & Recreation Facilities | ABCDE | Various | High Mast Lighting; Replacement or additions of new timber poles, lighting fixtures, electrical boxes, wiring, and bulbs at playgrounds, parks, ball fields, and community areas. | 7532, 12750,13734, 3282 | Three Fold Consultants, Inc. | Frischhertz Electric | 327920 | 327920 | Contract Closure
Facilities | NORD High Mast Lighting Group 3 | NRD129 | Parks & Recreation Facilities | ABCDE | Various | High Mast Lighting; Replacement or additions of new timber poles, lighting fixtures, electrical boxes, wiring, and bulbs at playgrounds, parks, ball fields, and community areas. | 10626, 3807, 5797, 3877 | Three Fold Consultants, Inc. | Frischhertz Electric | 374715 | 374715 | Contract Closure
Facilities | NORD High Mast Lighting Group 4 & 5 | NRD135 | Parks & Recreation Facilities | ABCDE | Various |  | 13790, 4930, 8036, 10616 | Three Fold Consultants, Inc. | TBD | 376836 | 376836 | Design | Q1 2011
Facilities | Norman Mayer Library Design-Build | DBL003 | Public Libraries | D | 2098 Foy St. | Replacement facility is designed as a "Music Branch" and includes a collection of print and non-print materials, enterprise space, children's area and WI-Fi hotspot. | 7579 | Gibbs Construction Design-Build | Gibbs Construction Design-Build | 5720105 | 5720104 | Construction | Q3 2011
Facilities | Norwood Thompson Playground | NRD140 | Parks & Recreation Facilities | B | 7200 Forshey St. | Minor renovations to NORD playground. | 6707 | TBD | TBD | 700000 | 700000 | Contracting | Q2 2011
Facilities | Oliver Bush Playground | NRD057 | Parks & Recreation Facilities | E | 2500 Caffin St. | Community basketball, baseball, and tennis recreational area in lower ninth ward community. | 4923, 1730 | Verges Rome Architects, APC | TBD | 1396157 | 750643 | Design | Q2 2011
Public Works | Opelousas Street Extension (Behrman Avenue to O'Bannon St.) | DPW322 | Roadways | C |  | Rehabilitation of roadway by milling existing surface and overlay with new asphalt, including pre-milling patching repairs as well as adjustment of utility manholes, where applicable. |  | C & S Consultants | Barriere Construction Co. | 3335000 | 3335000 | Construction | Q2 2011
Public Works | Oretha Castle Haley Blvd Streetscape (Felicity St. - Martin Luther King Jr) | DPW140 | Streetscapes | B | Felicity St. - Martin Luther King Jr | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Krebs, Lasalle & Lemieux |  | 300000 | 300000 | Design | Q2 2011
Public Works | Orleans Ave. (N. Claiborne Ave - City Park Ave.) | DPW145 | Roadways | A |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | Boh Brothers Construction Company, L.L.C. | 10553651 | 10553651 | Construction | Q2 2011
Facilities | Oscar Medrano Clinic | HCL003 | Health Clinics | C | 517 N Rampart St. |  | 7728 | Duplantier & Meric Architects LLC | TBD | 566898 | 566898 | Design | Q2 2011
Public Works | Paris Ave. (I-610 - Mirabeau Ave) | DPW147 | Roadways | D |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | RMD Holdings Ltd | 2364948 | 2364948 | Construction | Q2 2011
Public Works | Park Island Bridge over Bayou St. John | DPW150 | Roadways | AD |  | Bridge reconstruction. |  | Rahman & Associates | Cycle Construction | 2085853 | 2085853 | Construction | Q1 2010
Facilities | Parks & Parkways Fuel Island | QH043 | Parks & Recreation Facilities | D | 2829 Gentilly Blvd. | Repair of Fuel Island at 2829 Gentilly for Parks & Parkways & EMD |  | Byron J. Stewart and Associates | TBD | 60000 | 60000 | Design | Q3 2011
Facilities | Parks & Parkways Gentilly Facility | RPP001 | Parks & Recreation Facilities | D | 2829 Gentilly Blvd. | Renovation of Hurricane Katrina damages to the facilities that house the city's Parks & Parkways Department. | 3103 | Byron J. Stewart and Associates | TBD | 3500209 | 3500209 | Contracting | Q2 2011
Public Works | Patching Repairs - City Park | PWF006 | FEMA Eligible | A |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17367 | Department of Public Works | Fleming Construction Company, L.L.C. | 366217 | 366217 | Contract Closure
Public Works | Patching Repairs - Filmore | PWF013 | FEMA Eligible | D |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17107 | Department of Public Works | Durr Heavy Construction, L.L.C. | 2181931 | 2181931 | Contract Closure
Public Works | Patching Repairs - Gentilly Woods | PWF018 | FEMA Eligible | D |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17101 | Department of Public Works | Durr Heavy Construction, L.L.C. | 521674 | 521674 | Contract Closure
Public Works | Patching Repairs - Lake Terrace & Oaks | PWF023 | FEMA Eligible | D |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17370 | Department of Public Works | Durr Heavy Construction, L.L.C. | 661342 | 661342 | Contract Closure
Public Works | Patching Repairs - Lakeshore - Lake Vista | PWF024 | FEMA Eligible | A |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17358 | Department of Public Works | Boh Brothers Construction Company, L.L.C. | 957181 | 957181 | Contract Closure
Public Works | Patching Repairs - Lower Ninth Ward | PWF030 | FEMA Eligible | E |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17156 | Department of Public Works | Boh Brothers Construction Company, L.L.C. | 2846167 | 2846167 | Contract Closure
Public Works | Patching Repairs - Marlyville & Fontainbleau | PWF032 | FEMA Eligible | AB |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17372 | Department of Public Works | Fleming Construction Company, L.L.C. | 3499800 | 3499800 | Contract Closure
Public Works | Patching Repairs - Navarre | PWF036 | FEMA Eligible | A |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17109 | Department of Public Works | Fleming Construction Company, L.L.C. | 870164 | 870164 | Contract Closure
Public Works | Patching Repairs - Roads and Streets in Miscellaneous Blocks City Wide | PWF056 | FEMA Eligible | ABCDE |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17414 |  |  | 335666 | 335666
Public Works | Patching Repairs - West End | PWF053 | FEMA Eligible | A |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17106 | Department of Public Works | Harris Builders, LLC | 2423990 | 2423990 | Contract Closure
Public Works | Patching Repairs - West Lake Forest | PWF054 | FEMA Eligible | DE |  | Patching repairs of streets and sidewalks damaged by storm waters and debris removal. | 17200 | Department of Public Works | Fleming Construction Company, L.L.C. | 459285 | 459285 | Contract Closure
Facilities | Pontchartrain Park and Lights | NRD040 | Parks & Recreation Facilities | D | 5721 Press Drive, 6455 Press Drive, 4820 Hayne Blvd | Complete renovation of concession bldg.& lights | 18049 | St Martin Brown & Associates, LLP | W.L. Wyman Constructors Co., LLC | 2552200 | 2552200 | Construction | Q3 2011
Facilities | Pontchartrain Park Enhancements | NRD123 | Parks & Recreation Facilities | D | 5721 Press Drive, 6455 Press Drive, 4820 Hayne Blvd | Part of the Ponchartrain Park community golf course renovation. Added ground enhancements to the existing facility. |  | SCNZ Architects, LLC | TBD | 500000 | 500000 | Design | Q3 2011
Public Works | Poydras St (Claiborne Ave - Broad St) (Mid-City) | DPW157 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Meyer Engineers | Barriere Construction Co. | 1770953 | 1770953 | Warranty
Public Works | Poydras St (Carondelet St - Camp St) | DPW158 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 123759 | 123759 | Contract Closure
Public Works | Poydras St (LaSalle St - Loyola Ave) | DPW159 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 317370 | 317370 | Contract Closure
Public Works | Press Dr (US 90 - Robert E. Lee Blvd) Bikeways | DPW255 | Roadways | D |  | Install new pavement markings and signage |  | Department of Public Works | Gulf Industries / Vulcan Industries | 22440 | 22440 | Construction | Q2 2010
Public Works | Press Drive Streetscape (Chef - Leon C Simon) | DPW233 | Streetscapes | D | Chef - Leon C Simon | Landscaping along Press Drive |  | Spackman, Mossop & Michaels |  | 200000 | 200000 | Bid & Award | Q1 2011
Community Development | Public Greenspace Tree Replacement - Phase I | OPS197 | Other Public Spaces | ABCDE | Citywide | Beautification project |  | Parks & Parkways | Bayou Tree Services, Inc. | 750000 | 750000 | Construction | Q1 2011
Community Development | Public Greenspace Tree Replacement - Phase II | OPS198 | Other Public Spaces | ABCDE | Citywide | Beautification project |  | Parks & Parkways | TBD | 1250000 | 1250000 | Design | Q2 2011
Community Development | Reinventing the Crescent | NRD142 | Parks & Recreation Facilities | C | Riverfront (Poland St. - Esplanade Ave.) | Extensive redevelopment of the east bank riverfront from Jackson Ave. to the Industrial Canal includes recreational, entertainment and exhibit attractions. |  | Eskew, Dumez & Ripple | Landis Construction Company, LLC | 30000000 | 30000000 | Construction | Q3 2012
Public Works | Reinventing the Crescent Downriver Park-N Peters (St. Philip-St. Ferdinand) Chartres (Piety-Gallier) | DPW320 | Roadways | C |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Department of Public Works | Boh Brothers Construction Company, L.L.C. | 999790 | 999790 | Contract Closure
Public Works | Robert E. Lee Blvd (St. Bernard Ave - Paris Ave) Bikeways | DPW254 | Roadways | AD |  | Install new pavement markings and signage. |  | Department of Public Works | Gulf Industries / Vulcan Industries | 14630 | 14630 | Construction | Q2 2010
Public Works | Robert E. Lee Blvd (Perlita Dr - Chatham Dr) and Paris Ave. (Robert E. Lee - Aviators) Streetscape | DPW241 | Streetscapes | D | Robert E. Lee Blvd (Perlita Dr - Chatham Dr) and Paris Ave. (Robert E. Lee - Aviators) | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | GEC |  | 500000 | 500000 | Design | Q2 2011
Facilities | Robert E. Smith Library Design-Build | DBL004 | Public Libraries | A | 6301 Canal Blvd. | Replacement facility is designed as a "Community Branch" Library including Wi-Fi hotspot, enterprise space and meeting rooms. | 7421 | Gibbs Construction Design-Build | Gibbs Construction Design-Build | 4284069 | 4284069 | Construction | Q3 2011
Facilities | Rosa Keller (Broadmoor) Library | LIB003 | Public Libraries | B | 4300 S Broad St. | Replacement facility for library and major renovation of historic house to a community center with enterprise zone. | 7847 | Eskew, Dumez & Ripple | Ryan Gootee General Contractors | 5201990 | 5201990 | Construction | Q4 2011
Facilities | Rosenwald Center | NRD042 | Community Centers | B | 1120 S Broad St. | Replacement facility to include gym, community center and restore the pool | 13734 | Wink Design Group | TBD | 6129469 | 6118601 | Design | Q3 2011
Public Works | S. Jeff. Davis (M. L. King Jr. - Howard) | DPW176 | Roadways | B | (M. L. King Jr. - Howard) | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Buchart Horn | TBD | 4670446 | 4670446 | Bid & Award | Q2 2011
Community Development | Saenger Theatre Renewal Project | OPS196 | Other Public Spaces | ABCDE | 801 N Rampart St. | Major historic renovation of entertainment venue. |  | TBD | TBD | 13000000 | 13000000 | Construction | Q3 2012
Facilities | Sam Bonart Playground | NRD043 | Parks & Recreation Facilities | E | 1200 Forstall St. | Repair of facility to Pre-Katrina function. Repair of concessions, fields and basketball shelter. | 3759 | Three Fold Consultants, Inc. | TBD | 586606 | 586606 | Design | Q2 2011
Facilities | Sam Bonart Pool Repairs | NRD161 | New Orleans Recreation Department | E | 1200 Forstall St. |  |  | Capital Projects | TBD | 85921 | 85921 | Bid & Award | Q1 2011
Facilities | Sampson Pool Repairs | NRD158 | New Orleans Recreation Department | E | 3185 Louisa St. |  |  | Capital Projects | TBD | 99772 | 99772 | Bid & Award | Q1 2011
Facilities | Sanchez (Copelin-Byrd) Center | NRD009 | Community Centers | E | 1616 Caffin Ave. | Replacement facility to include gym, community center, health clinic, police substation. | 18909 | Perez, APC | TBD | 11623099 | 11623099 | Design | Q4 2011
Community Development | Sanchez (Copelin-Byrd) Center Land Acquisition | NRD139 | Community Centers | E | 1600 Flood St. | Land Acquisition for pool. |  | TBD | TBD | 1000000 | 1000000 | Design
Facilities | Sanchez (Copelin-Byrd) Pool | NRD010 | Community Centers | E | 1616 Caffin Ave. | New facility to include new pool and pool facility to include shower/lockers/restrooms. |  | Perez, APC | TBD | 3181368 | 3181367 | Design | Q4 2011
Public Works | School Zone Flashing Beacons | PWF055 | FEMA Eligible | ABCDE |  | Repair and/or replacement of damaged school zone flashers with new solar-powered flashers | 17404 | Department of Public Works | Jack Harper Contractor, Inc. | 1793456 | 1793456 | Contract Closure
Public Works | St. Anthony Path Landscape (Mirabeau - Pelopidas) | DPW187 | Streetscapes | CD | Mirabeau - Pelopidas | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | GEC |  | 400000 | 400000 | Bid & Award | Q2 2011
Public Works | St. Bernard Ave (Claiborne Ave - North Miro St) | DPW188 | Streetscapes | ACD | Claiborne Ave - North Miro St | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Buchart Horn |  | 600000 | 600000 | Design | Q2 2011
Public Works | St. Bernard Ave. (I-610 - Filmore Ave.) | DPW189 | Roadways | AD |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Stanley | RMD Holdings Ltd | 3995250 | 3995250 | Construction | Q2 2011
Facilities | St. Bernard Pool Repairs | NRD159 | New Orleans Recreation Department | D | 1500 Lafreniere St. |  |  | Capital Projects | TBD | 48500 | 48500 | Bid & Award | Q1 2011
Public Works | St. Charles Ave (Nashville Ave - S. Carrollton Ave) | DPW190 | Roadways | A |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Shread | Boh Brothers Construction Company, L.L.C. | 3252163 | 3252163 | Warranty
Public Works | St. Charles Ave. (Canal St - US 90) | DPW191 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Rahman & Associates | Boh Brothers Construction Company, L.L.C. | 1617455 | 1617455 | Contract Closure
Facilities | St. James Playground Equipment Donation | NRD148 | Parks & Recreation Facilities | D | 2400 Filmore | Surface installation for work & equipment donation program. |  | NORD | TBD | 35000 | 35000 | Closeout
Public Works | St. Roch and St. Claude Roadway Improvements (St. Claude Ave. - N. Roman St.) | DPW185 | Roadways | C |  | Rehabilitation of roadway by milling existing surface and overlay with new asphalt, including pre-milling patching repairs as well as adjustment of utility manholes, where applicable. |  | Department of Public Works | Julien Engineering & Consulting, Inc. | 1476000 | 1476000 | Contract Closure
Facilities | St. Roch Market | OPS005 | Other Public Spaces | C | 2381 St Claude Ave. | Restoration of the historic neighborhood former food and produce market facility along the St. Claude Corridor. | 13735 | Lee Ledbetter & Associates,APC | TBD | 2783904 | 2783903 | Design | Q3 2011
Facilities | St. Roch Neutral Ground | OPS190 | Other Public Spaces | C | 2381 St Claude Ave. | Beautification of neutral grounds and Art Walk that connect the St. Roch Market and St. Roch Park Facilities |  | Parks & Parkways | TBD | 389680 | 389680 | Design | Q3 2011
Facilities | St. Roch Pool / Park | OPS189 | Parks & Recreation Facilities | C | 1800 St. Roch Ave. | Renovation of the NORD operated pool facility and adjacent park facility including services buildings and Community park grounds. | 3980 | Lee Ledbetter & Associates,APC | TBD | 1599745 | 1599744 | Design | Q3 2011
Facilities | Stallings Gentilly Pool Repairs | NRD160 | New Orleans Recreation Department | C | Gentilly & Lapeyrouse St. |  |  | Capital Projects | TBD | 68175 | 68175 | Bid & Award | Q1 2011
Facilities | Stallings St. Claude Community Center | NRD011 | Community Centers | C | 4300 St Claude Ave. | New Center will include basketball court, multi-purpose rooms for dance, music and activities. Major renovations to pool and pool building including restrooms/lockers/showers. | 4835 | Lee Ledbetter & Associates,APC | TBD | 6029368 | 6029368 | Design | Q3 2011
Facilities | Taylor Pool Repairs | NRD156 | New Orleans Recreation Department | B | 2600 S Roman Street |  |  | Capital Projects | TBD | 9800 | 9800 | Bid & Award | Q1 2011
Public Works | Tchoupitoulas St (Canal St - Calliope St) | DPW195 | Roadways | B |  | Rehabilitation of roadway by milling existing surface and overlay with new asphalt, including pre-milling patching repairs as well as adjustment of utility manholes, where applicable. |  | Watson Ricks, LLC | TBD | 1765551 | 1765551 | Design | Q1 2011
Facilities | Treme Center | OPS156 | Community Centers | C | 900 N Villere St. | Major renovation of the existing community center including repairs to the pool, gymnasium and enhancements for handicap accessibility to the facility. | 4429 | Hamilton Anderson Associates, Inc. | TBD | 4557131 | 4557131 | Design | Q1 2011
Public Works | Tulane Ave and Jeff. Davis Pkwy Streetscape (Baudin St, Clark(sou D'hemecourt St)) | DPW196 | Streetscapes | B | Baudin St, Clark(sou D'hemecourt St) | May include sidewalk or other pedestrian walkway improvements, bikeways, traffic and pedestrian signage or signalization, landscaping, lighting, or public art. |  | Buchart Horn | 3C's Properties | 300000 | 300000 | Bid & Award | Q1 2011
Community Development | Tulane University Community Health Clinic | HCL015 | Health Clinics | ABC | 711 N Broad St. | Neighborhood health clinic. |  | TBD | TBD | 2000000 | 2000000 | Bid & Award | Q2 2011
Public Works | Urquhart St. (Elysian Fields Ave - Franklin Ave) | DPW242 | Roadways | C |  | Reconstruction of existing roadway, including the replacement of affected utilities. |  | C & S Consultants | TBD | 3541073 | 3541073 | Construction | Q3 2011
Community Development | VA Medical Center | HSP002 | Hospital Facility | ABCDE | Canal Blvd. between N Galvez & S Rocheblave) | Major new construction of VA hospital in hospital complex. |  | TBD | TBD | 75000000 | 75000000 | Construction | Q1 2011
Public Works | Veterans Admin. Medical Ctr Infrastructure Improvements (Canal, S Claiborne, Tulane, & S Rocheblave) | DPW296 | Roadways | B | Canal, S Claiborne, Tulane, & S Rocheblave | Reconstruction of existing roadway, including the replacement of affected utilities. |  | N-Y Associates Architects | Wallace C. Drennan | 12000000 | 12000000 | Construction | Q4 2011
Public Works | Washington (S. Broad St. - S. Carrollton Ave.) | DPW205 | Roadways | B |  | Rehabilitation of existing roadway, including milling and overlay with new asphalt. |  | Meyer Engineers | Barriere Construction Co. | 3104768 | 3104768 | Warranty
Facilities | Wesley Barrow Stadium | NRD049 | Parks & Recreation Facilities | D | 6500 Press Dr. | Baseball Stadium in Ponchartrain Park community. Major renovation to field and viewing stands. | 15951, 4526 | SCNZ Architects, LLC | TBD | 4429566 | 4429566 | Design | Q2 2011
Facilities | West End Park | OPS178 | Parks & Recreation Facilities | A | South Rd | Minimal repairs to park. | 1028 | Three Fold Consultants, Inc. | TBD | 92730 | 92730 | Contracting | Q1 2011
Public Works | West Roadway (Lake Marina Ave - South Roadway) | DPW328 | Roadways | D |  | Asphalt pavement, base repair and curb replacement |  |  | Boh Brothers Construction Company, L.L.C. | 256500 | 256500 | Construction | Q3 2010
Public Works | Whitney Ave & L.B. Landry (Mardi Gras Blvd - Patterson Dr) Bikeways | DPW251 | Roadways | C |  | Install new pavement markings and signage |  | Department of Public Works | Gulf Industries / Vulcan Industries | 41195 | 41195 | Construction | Q2 2010
Facilities | Whitney Young Pool Repairs | NRD097 | New Orleans Recreation Department | A | 6500 Magazine St |  | 2944 | Capital Projects | TBD | 15500 | 15500 | Bid & Award | Q1 2011
Facilities | Wisner Playground | NRD067 | Parks & Recreation Facilities | B | 4877 Laurel St. | Minor repairs to playground lighting/major repairs future | 10746, 2245 | HMS Architects, APC | TBD | 281124 | 281124 | Contracting | Q2 2011
Public Works | Wright Road (Chef Menteur Blvd - Dwyer Rd) | DPW213 | Roadways | E | (Chef Menteur Blvd - Dwyer Rd) | Reconstruction of existing roadway, including the replacement of affected utilities. |  | Three Fold Consultants, Inc. | TBD | 10017518 | 10017518 | Design | Q1 2011
Facilities | Youth Study Center | PSF001 | Criminal Justice Facilities | A | 1100 Milton St. | Full replacement of the existing juvenile detention center damaged by Hurricane Katrina. | 12621 | Mathes Brierre Architects, APC | TBD | 26334492 | 25492236 | Design | Q3 2012
[10 empty] | 824427532 | 822865028