## Slide 1: BlightStat
City of New Orleans
November 4, 2010

## Slide 2: Agenda
Introductions and welcome
Customer Service
Inspections
Hearings
Abatement
Disposition

## Slide 3: Introductions and Welcome
On September 30, Mayor Landrieu announced his blight strategy, which pledges to reduce blighted properties by 10,000 in three years
The blight strategy prioritizes code enforcement and code lien sales (Sheriff’s sales) as City’s key tool to police blighted homes, compel property owners to rehabilitate their properties, remediate blighted conditions, and foreclose and sell those properties that remain blighted
BlightStat will be the principle vehicle that the City will use manage and monitor the implementation of the Mayor Landrieu’s blight eradication strategy, and report progress to the public
In these meetings, senior staff will meet with front-line department heads and program managers to discuss progress in meeting goals through the analysis of performance metrics
These are working meetings, intended to provoke constructive dialogue on what’s working, what’s not, and what the City needs to do to improve
BlightStat will be one of several “NOLAStat” initiatives Mayor Landrieu will use to improve performance, accountability, and transparency in city government

## Slide 4: Customer Service - Code Enforcement
Chart: Response Times to Customer Complaints October 18 - 29
| Inspected within Zero to Five Days | Inspected within Six to Fifteen Days | Not Inspected Within Fifteen Days
 | 0.46862 | 0.037657 | 0.49372
 | Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29)
Customer Service |  |  | 
Calls Recieved for Blighted Property |  | 444 | 270
Calls for New Properties Requiring Inspections |  | 123 | 102
Case Opened and Assigned to Inspector Within 24 Hours | 100% | 100% | 100%

## Slide 5
Chart: 
| Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29)
Structure Inspections | 800 | 213 | 415

## Slide 6
Chart: 
| Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29)
Lots Inspected | 400 | 403 | 315

## Slide 7
Chart: 
| Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29)
Inspections per inspector per day | 12 | 4 | 8

## Slide 8
Chart: 
| Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29)
Inspections completed in Accela | 1 | 0.39 | 0.58

## Slide 9
Chart: Code Enforcement Hearings Oct 18 - 29
| Guilty (No Show) | Guilty (Show) | Dismissed | Reinspection | In Compliance
 | 24 | 6 | 5 | 113 | 20

## Slide 10
Chart: Health Court Hearings Oct 18 - 29
| Guilty (Show and No Show) | Dismissed | Reset
 | 157 | 41 | 11

## Slide 11
Chart: 
| Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29)
Total Combined Hearings | 450 | 413 | 377
A total of a $788,925 in code violation fines have been levied since October 1, 2010

## Slide 12: Abatement – Code Enforcement and Environmental Health
 | Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29) | Variance from prior period | Variance from target
Abatement |  |  |  |  | 
Demolitions | 50 | 24 | 12 | -50% | -76%
Grass Cuttings | 150 | 67 | 153 | 128% | 2%

## Slide 13: Sheriff Sale Review
 | Target per 2 Week Period | Actual Performance (Oct. 1 - 15) | Actual Performance (Oct. 18 - 29) | Variance from prior period | Variance from target
Sheriff Sales |  |  |  |  | 
Files Reviewed | 100 | 156 | 161 | 3% | 61%
Files Rejected |  | 131 | 61 | -53% | 
Files Approved |  | 5 | 16 | 220% | 
Files Moved to CDC |  | 5 | 7 | 40% | 
Scheduled for Sheriff Sale | 10 | 3 | 0 |  | -70%
Files Awaiting Final Determination |  | 20 | 84 | 320% | 

## Slide 14
Chart: Reasons for Rejecting Files for Sheriff Sales October 18 - 29
| Homestead Exemption | Noticing Problems | Sold to NORA or Road Home | Other
 | 13 | 10 | 12 | 26

## Slide 15: LLT Property Disposition - NORA
 | Total to Q3 2010 | Q3 2010 | Q4 2010 (Est)
Acquisition of Blighted Properties |  |  | 
LLT (Road Home) | 4990 | 35 | 20
NORA/NORU Realm Land Bank | 388 | 2 | 0
Disposition Completed |  |  | 
Total LLT Closings | 728 | 126 | 135
Closings by type - LND | 294 | 78 | 75
Closings by type - Individual Sales | 125 | 17 | 20
Closings by type - Development & other | 309 | 31 | 40
Total NORA/NORU Closings | 75 | 6 | 19
Closing by type- LND | 16 | 1 | 3
Closing by type - Individual Sales | 2 | 2 | 1
Closing by type - Development & other | 57 | 3 | 15
Inventory Remaining |  |  | 
LLT (Road Home) |  | 4262 | 4147
NORA/NORU Realm Land Bank |  | 313 | 294
LLT C Files |  | 160 | 150
Pending Transactions |  |  | 
Ready to Close | 132 |  | 
Signed Purchase Agreement | 450 |  | 
Outcomes of Sales |  |  | 
New/Renovated Housing Complete | 107 |  | 
Property Expansion/Growing Home | 100 |  | 
Alternative Uses | 1 |  | 
Work in Progress | 203 |  | 
LLT C Files (maintained by LLT) | 160 |  | 
Most Recent Closings (pre-inspection) | 132 |  |